HELLO GORGEOUS MED SPA

Zero-Budget SEO Recovery Plan

May 18 – May 25, 2026  •  Total cost: $0  •  Owner: Dani  •  Dev: Eric + Claude Code

# The Deal

No paid ads. No paid tools. No agency. Just the moves a small business owner can make herself, using time and the platforms she already has.

Three facts from this morning's SEO audit:

- Hello Gorgeous owns Morpheus8 Burst Oswego in search — three of the top three results are yours.

- Hello Gorgeous competes well on "best med spa Oswego" — multiple pages rank.

- HER Aesthetics is beating Hello Gorgeous on Botox search — your highest-volume service.

The free moves don't move the needle as fast as paid ads, but they compound. Yelp + GBP optimization, technical SEO, one strong landing page, citation cleanup, and a review loop are the same plays a $5,000/month agency would run — they'd just charge for them.

Realistic timeline at zero spend: Days 1-7 lock in the foundation. Days 8-30 the foundation starts working. Days 31-90 you see real ranking movement. By Day 90, you should be ranking top 3 organically on Botox Oswego.

# Week at a Glance

| Day | Task | Owner | Time |
| --- | --- | --- | --- |
| Day 1 Mon | Claim/optimize Yelp business listing — we're #4 for Botox, this is the fastest fix | Dani | 1 hour |
| Day 1 Mon | Audit Google Business Profile — add missing photos, services, posts, Q&A | Dani | 90 min |
| Day 2 Tue | Review request blitz — text 10 happy clients (Google + Yelp) | Dani | 45 min |
| Day 2 Tue | Respond to every existing Google + Yelp review (signals active business) | Dani | 60 min |
| Day 3 Wed | Eric: schema markup, meta titles, sitemap, page speed audit | Eric | 3-4 hrs |
| Day 4 Thu | Write definitive 'Botox in Oswego' landing page (Claude drafts, you edit) | Dani+Claude | 90 min |
| Day 5 Fri | Publish Botox page + push to IG, FB, Google Business Post, email blast | Dani+Eric | 60 min |
| Day 6 Sat | Local citations: BBB, Bing Places, Apple Maps, Patch, vendor directories | Dani | 90 min |
| Day 7 Sun | Baseline measurement — record rankings, GBP insights, set up free tracking | Dani | 30 min |

Eric's total time: ~4 hours of dev work (Day 3) + 30 min for publish/redirect on Day 5. Your total time: ~7 hours across the week. Cost: $0.

# Day 1 (Monday) — Free Platforms

## Task 1.1 — Yelp profile (1 hour)

Why: Yelp's algorithm heavily weights profile completeness, photo count, owner activity, and Yelp-specific review volume. Free to fix. Currently ranks Hello Gorgeous #4 for Botox in Oswego.

Action steps

- Go to biz.yelp.com — verify ownership of Hello Gorgeous listing

- Upload 25+ photos: storefront, treatment rooms, before/afters (with consent), team headshots, InMode devices, Best of Oswego awards

- Complete 'About this Business' in your brand voice (rewrite from your website if needed)

- Add every service offered as a separate menu item

- Set business hours, holiday hours, parking info

- Add 'Specialties': Morpheus8 Burst, Solaria CO2, Quantum RF, full-authority NP on site

- Respond to every existing Yelp review — good and bad. Owner activity = ranking signal

## Task 1.2 — Google Business Profile (90 min)

Why: GBP determines whether you appear in the Map Pack — the boxed top-3 results below the map. The Map Pack gets ~44% of all local clicks. This is the single highest-leverage free asset you control.

Action steps

- business.google.com → Hello Gorgeous

- List every service individually: Botox, Dysport, Jeuveau, Dermal Fillers, Morpheus8 Burst, Quantum RF, Solaria CO2, Semaglutide, Tirzepatide, BioTE, Peptide Therapy, IV Therapy, etc.

- Add 10+ Q&As yourself: 'Do you take insurance?', 'Do you have a nurse practitioner on site?', 'How much is Botox?', 'Do you offer Morpheus8 Burst?' — these become rich snippets

- Upload 30+ photos, tag one per service

- Post 3 Google Business Posts this week: Botox special, Morpheus8 Burst education, Ryan on-site NP intro

- Add Fresha booking link as primary booking URL

- Enable messaging so clients can text from Google search

Set primary category: 'Medical Spa'. Secondary: Skin Care Clinic, Weight Loss Service, Wellness Center. Wrong categories kill local rankings.

# Day 2 (Tuesday) — Reviews, the Free Ranking Signal

## Task 2.1 — Review request blitz (45 min)

Why: Reviews are the single biggest free ranking signal across both Google and Yelp. Volume, recency, and platform-specific reviews all matter. 4.9 / 47 Google reviews is strong, but more is better, and Yelp likely has fewer.

Action steps

- Pull last 30 days of happy clients from Fresha (treatments completed, no complaints)

- Identify 10 — half get the Google ask, half get the Yelp ask

- Send the templated text below. Goal: 5 new Google + 3 new Yelp reviews this week

- Ask for honest reviews, not 5-star — Yelp filters anything that looks solicited

Text template — Google

Hi [name]! It's Dani from Hello Gorgeous — hope you're loving your
[treatment]! If you have 60 seconds, would you share your honest
experience on Google? Reviews mean everything to a small business
like ours. Link: [shortened Google review URL]
No pressure either way — thanks for being a HG client. xo

Text template — Yelp

Hi [name]! Dani from Hello Gorgeous. Quick favor — would you share
your honest experience on Yelp if you have a minute? Yelp matters
more than people realize for local businesses. Link: [Yelp URL]
Always appreciate you. xo

## Task 2.2 — Respond to every existing review (60 min)

Why: Owner response rate is a ranking signal on Google and a major one on Yelp. Most med spas don't respond. Be the one that does. Cost: zero, just time.

Response framework

- 5-star: thank them by name, mention the specific treatment, invite them back. 1-2 sentences.

- 4-star: thank them, ask what would have made it 5-star, offer to talk if they want. Show you care.

- 3-star or below: thank them for honest feedback, acknowledge specifically what they said, offer to discuss privately. Never argue. Never defend. Always invite continued conversation off-platform.

Every response is a public ad for your service. A graceful response to a tough review wins more clients than the original review costs you.

# Day 3 (Wednesday) — Eric's Technical SEO Sprint

Owner: Eric (with Claude Code). Time: 3-4 hours. Cost: $0 — uses tools you already have.

Eric, this section is written for you. Read it all, build the implementation plan, execute through the existing Next.js / Vercel setup. Target: hellogorgeousmedspa.com.

## Task 3.1 — Schema.org structured data (90 min)

Add JSON-LD structured data to homepage and every service page. Schema is how Google understands what your business is and what services you offer. Without it, you're invisible to rich results.

Schemas to add

- MedicalBusiness (homepage) — name, address, phone, hours, geo, founder, medical specialty, services offered, aggregateRating

- MedicalProcedure (each treatment page) — name, procedureType, bodyLocation, performer (linked to MedicalBusiness)

- Person (Ryan Kent, FNP-BC) — name, jobTitle, worksFor (linked to MedicalBusiness), knowsAbout

- FAQPage (any page with FAQ — Botox, Morpheus8, etc.) — wraps each Q&A so Google shows them as expandable results

- BreadcrumbList (every page) — helps Google understand site hierarchy

Example: MedicalBusiness schema for homepage

{
  "@context": "https://schema.org",
  "@type": "MedicalBusiness",
  "name": "Hello Gorgeous Med Spa",
  "image": "https://www.hellogorgeousmedspa.com/og-image.jpg",
  "address": {
    "@type": "PostalAddress",
    "streetAddress": "74 W Washington St",
    "addressLocality": "Oswego",
    "addressRegion": "IL",
    "postalCode": "60543",
    "addressCountry": "US"
  },
  "geo": { "@type": "GeoCoordinates", "latitude": 41.6836, "longitude": -88.3528 },
  "telephone": "+1-630-636-6193",
  "openingHours": ["Mo-Sa 09:00-19:00"],
  "medicalSpecialty": ["Dermatology", "Aesthetics", "WeightManagement"],
  "aggregateRating": { "@type": "AggregateRating", "ratingValue": "4.9", "reviewCount": "47" },
  "url": "https://www.hellogorgeousmedspa.com"
}

## Task 3.2 — Meta titles & descriptions audit (60 min)

Every page needs a unique title (50-60 chars) and meta description (150-160 chars) with the target keyword in the first half. Audit every page; rewrite where weak.

Target keywords by page

- / (homepage) — 'best med spa oswego il'

- /botox-oswego-il — 'botox oswego' (priority — see Day 4)

- /services/morpheus8-burst — 'morpheus8 burst oswego'

- /services/quantum-rf — 'quantum rf oswego' (no competition — easy win)

- /services/solaria-co2 — 'solaria co2 oswego' (no competition — easy win)

- /services/weight-loss — 'medical weight loss oswego', 'semaglutide oswego', 'tirzepatide oswego'

- /services/hormone-therapy — 'hormone therapy oswego', 'biote oswego'

## Task 3.3 — Sitemap.xml + robots.txt + Search Console (30 min)

- Verify sitemap.xml exists at /sitemap.xml and includes every public page

- Submit/resubmit sitemap to Google Search Console (free)

- Verify robots.txt isn't blocking any service pages by accident

- Set up Bing Webmaster Tools (free) — ~7% of search traffic, takes 5 minutes

## Task 3.4 — Core Web Vitals quick fixes (30 min)

Free check via Google PageSpeed Insights (pagespeed.web.dev). Google uses Core Web Vitals as a ranking factor. Easy wins:

- Compress + lazy-load all images below the fold (Next.js next/image should already do this)

- Eliminate render-blocking JavaScript on the homepage

- Load booking widget async, not blocking the page render

Eric's Wednesday deliverable: schema deployed, meta titles updated, sitemap re-submitted, Bing set up, PageSpeed score 85+ on mobile for homepage and /botox-oswego-il.

# Day 4 (Thursday) — Steal the Botox Keyword (Free)

Owner: Dani (with Claude). Time: 90 minutes. Cost: $0.

Highest-leverage piece of content this week. HER Aesthetics has three pages in the top 5 for 'Botox Oswego' because they have dedicated, focused content. Hello Gorgeous has /services/botox-dysport-jeuveau and /botox-oswego-il, but neither is winning. We'll consolidate into one page that does.

## What makes a winning Botox landing page in 2026

- Length: 1,500-2,500 words (HER's pages are ~1,200 — we'll go longer)

- Keyword density: 'Botox Oswego' or close variants 8-12 times in body, in H1, H2, meta title, meta description, image alt text

- Schema: MedicalProcedure + FAQPage schema

- Internal links: /services/morpheus8-burst, /about, /weight-loss

- External authority links: FDA approval pages for Botox, Dysport, Jeuveau

- Real differentiators: $10/unit pricing, Ryan FNP-BC on site, same-day appointments, Allē rewards

- Social proof: 3-5 real reviews embedded (with permission), the 4.9 / 47 aggregate

- Multiple CTAs: Fresha booking link, text us, call us

## Outline — Claude can draft each section in 5 minutes

- Hero: 'Botox in Oswego — From a Med Spa That Actually Has a Nurse Practitioner On Site' (differentiator in H1)

- 'Why Hello Gorgeous for Botox' — 4-5 bullets: NP on site, $10/unit, natural results, free consults, Allē rewards

- 'What is Botox / how it works' — 200 words of patient-friendly education (Google rewards educational content)

- 'Botox treatment areas we offer' — forehead, 11s, crow's feet, lip flip, gummy smile, masseter, neck bands, hyperhidrosis

- 'How much does Botox cost in Oswego' — pricing transparency. $10/unit. Outranks competitors who hide unit price

- 'What to expect at your first appointment' — step by step, 200 words

- 'Botox vs Dysport vs Jeuveau' — comparison table. Real answer to a real question = ranking gold

- 'Aftercare instructions' — 100 words

- FAQ section (FAQ schema) — 8-10 questions

- Closing CTA: 'Book your free Botox consultation in Oswego'

## Meta title and description

Title: Botox in Oswego, IL | $10/unit | Hello Gorgeous Med Spa
Description: Botox, Dysport, & Jeuveau in Oswego from $10/unit. Full-authority NP on site 7 days/week. #1 Best Med Spa. Free consultations. Same-day appointments available.

Once published, this is the canonical Botox page. Redirect /services/botox-dysport-jeuveau to it (301, not 302) so the new page inherits the older page's link equity.

# Day 5 (Friday) — Publish, Amplify, Index (Free)

## Task 5.1 — Publish the Botox page (Eric, 30 min)

- Deploy via Next.js / Vercel

- Verify schema renders correctly via Google's Rich Results Test (free tool)

- Submit URL to Google Search Console for priority indexing

- Submit URL to Bing Webmaster Tools

## Task 5.2 — Amplify on owned channels (Dani, 30 min)

Every channel here is free. Use them all.

- Instagram: carousel post with key Botox info, link in bio to new page

- Facebook: full link with thumbnail (less algo-friendly than reels, but worth it for a service page)

- Google Business Post: short 'New: Read everything you need to know about Botox in Oswego' with link

- Email blast to Fresha list (~2,221 contacts already loaded in your HelloGorgeous-EMAIL.html tool) — subject: 'The truth about Botox pricing in Oswego'

- Personal Facebook + Instagram stories the day of, the next day, and 3 days later — three impressions is the magic number

## Task 5.3 — Free backlinks (Dani, 30 min)

Backlinks are still the biggest ranking signal. Get 3-5 free quality ones pointing to the new Botox page:

- Patch.com news submission — Patch lets you submit free local news. Post about $10/unit Botox or your Best of Oswego win, link to the page

- Yellow Pages, MapQuest, Foursquare — free directory listings

- Cross-link from nopriorawthorization.com — your Dani bio on NPA links to your practice

- Allergan/Allē provider directory — they list you for free as a Botox provider, contact your Allergan rep

- InMode patient site provider locator — free, your InMode rep adds you

- BioTE provider locator — free, contact your BioTE rep

Vendor directories are the cheat code. You already buy from these companies — they WANT to list you. Each one is a free authority backlink.

# Day 6 (Saturday) — Free Citations Cleanup

'Citations' are mentions of your business name, address, and phone (NAP) across the web. Google trusts businesses whose NAP is consistent. Inconsistent NAP = lower rankings. Every platform below is free.

## Free citation checklist

- BBB (Better Business Bureau) — basic listing is free; only the 'Accredited' badge costs money. Skip the badge for now

- Bing Places — claim and verify (set up in Day 3 with Eric, complete it here)

- Apple Maps Connect — claim and verify (matters for iPhone users in Maps)

- Patch business listing — verify accuracy

- Healthgrades / RealSelf / RateMDs — provider profiles for Ryan especially

- Manta, Yellow Pages, Foursquare, MapQuest, Citysearch — free directory listings

- AmericanMedSpa.org provider directory — free listing if you're a member; if not, the basic listing is still free

- Allē provider locator (Allergan) — free, you already use Botox

- InMode patient site provider locator — free, you own three of their devices

Authoritative NAP to use everywhere (must be IDENTICAL, character for character)

Name:    Hello Gorgeous Med Spa
Address: 74 W Washington St
         Oswego, IL 60543
Phone:   (630) 636-6193
Website: https://www.hellogorgeousmedspa.com

Inconsistency hurts. 'Hello Gorgeous MedSpa' vs 'Hello Gorgeous Med Spa' registers as two different businesses to some directories. Pick one canonical name and use it everywhere.

# Day 7 (Sunday) — Measure (Free Tools)

You can't improve what you don't measure. Set up free tracking so we can see what's working in 30 days.

## Free tools to set up

- Google Search Console (free) — already should be set up; verify and pin top 10 keywords to track weekly

- Google Analytics 4 (free) — verify it's recording events; track 'booking_click' as a conversion

- Bing Webmaster Tools (free) — set up, submit sitemap

- Rank tracking — manual method: search each keyword in incognito Google + Chrome, record position. Takes 15 min weekly. No paid tool needed for this volume

## Baseline metrics to record this Sunday

- Google Search Console: impressions and clicks for 'botox oswego', 'morpheus8 oswego', 'med spa oswego', 'hello gorgeous'

- Google Business Profile insights: total searches, profile views, direction requests, calls, website clicks — last 30 days

- Yelp: profile views, click-throughs, review count

- Position tracking for these 10 keywords in incognito Google search:

- 1. 'best med spa oswego'

- 2. 'botox oswego'

- 3. 'morpheus8 burst oswego'

- 4. 'solaria co2 oswego'

- 5. 'quantum rf oswego'

- 6. 'medical weight loss oswego'

- 7. 'semaglutide oswego'

- 8. 'biote oswego'

- 9. 'med spa naperville'

- 10. 'dermal fillers oswego'

Save these baseline numbers in a Google Sheet. Re-check every Sunday. The first 2-3 weeks won't show much movement — that's normal. Real movement starts Week 4.

# Beyond Day 7: The Free 30/60/90 Roadmap

## Days 8-30 — Content cadence + reviews

- Publish 1 new educational blog post per week (Morpheus8 vs Profound, Solaria vs Halo, GLP-1 myths, hormone therapy basics). Claude drafts, you edit. 60-90 min each

- Respond to every new Google + Yelp review within 24 hours

- Continue review request blitz — target 30 new reviews across platforms by Day 30

- Eric: build out FAQ schema on every service page (each FAQ = potential rich result in Google)

- Start asking happy clients for video testimonials. One per week. Post to YouTube, embed on service pages. Free; massive ranking signal

## Days 31-60 — Free authority building

- Guest content: pitch local outlets (Patch, Naperville Sun, Aurora Beacon-News) on a 'Best Botox in Oswego' or 'Inside a Local Med Spa' angle. Free article = free backlink + brand authority

- Vendor partnerships: confirm you're listed in every directory of every brand you carry (Allergan, Allē, InMode, BioTE, Galderma, Merz). Free links from authoritative sites

- Begin geo-targeted landing pages: 'Botox in Naperville', 'Morpheus8 in Aurora'. Free traffic from nearby city searches

- Tap your network: every friend/colleague/professional contact with a website who would link to you. Often a simple 'Hey, do you have a recommended providers page? Would you add me?' email works

## Days 61-90 — Compounding

- YouTube channel: short patient education videos with Ryan + Dani. Google owns YouTube — video results rank in standard search. Free distribution platform

- Referral program: existing clients who refer get a service credit; new clients who come in via referral get $50 off. Word-of-mouth + reviews = compounding growth

- Audit Day 1 baseline: which keywords moved? Reinvest content effort in winners, abandon losers

- By Day 90, if Yelp ranking, GBP completeness, technical SEO, and content cadence are all done, you should be ranking top 3 organically on Botox Oswego — for $0 spent

# What's Different at $0 Spend

Honest assessment of what you trade off by not running paid ads:

## What you give up

- Immediate top-of-page visibility. Without Google Ads, you wait for organic to catch up. Realistic timeline to top 3 on Botox Oswego: 60-90 days vs. day-one with ads

- Brand defense. Without a brand-name campaign, a competitor could buy 'hello gorgeous med spa' as a keyword and show their ad above your organic result. Check this monthly by searching your own brand in incognito

- A/B testable conversion data on ad copy. Without ads, you don't get the rapid feedback loop on what messaging converts

## What you keep

- 100% of the SEO work that compounds forever — content, reviews, citations, schema, technical fixes

- Your relationship with clients — every review request is a personal touch, not a marketing automation

- Full ownership. You're not renting traffic from Google. You're building an audience

## When to reconsider paid ads

- If a competitor starts running brand-name ads against 'hello gorgeous' — defend immediately ($5/day brand campaign)

- If Day 90 organic results haven't moved your rankings on Botox Oswego — consider $25/day Botox campaign

- If a major launch (new device, new service, event) needs immediate visibility — short paid burst, then off

# Bottom Line

Total spend: $0. Total time: ~7 hours for you, ~4 hours for Eric, plus 60-90 min/week of content for the next 90 days. Total expected result by Day 90: top 3 organic ranking on Botox Oswego, 30+ new reviews, completed citation profile, and a publishing rhythm that compounds for years.

None of this requires you to spend a dollar. All of it requires you to show up consistently.

Want me to build the supporting pieces, all free?

- Full 'Botox in Oswego' landing page copy (Thursday's deliverable)

- The 10-message review request template pack (Google, Yelp, variations)

- Schema.org JSON files Eric can paste directly into Next.js

- 90-day content calendar with target keyword + outline for each weekly post